## Dashboard
PowerChart Build & Testing
# Order Sets Init. Build:
Total Order Sets:
Order Set Dashboard

## LinksAndMilestones
Document / Milestone | Description | Jan 27/23 | Feb 3/23 | Feb 10/23 | Feb 17/23 | Feb 24/23 | Mar 3/23 | Mar 10/23 | Mar 17/23 | Mar 24/23 | Mar 31/23 | Apr 7/23 | Apr 14/23 | Apr 21/23 | Apr 28/23 | May 5/23 | May 12/23
Northern Health Order Set Style Guide
Style Guide - Decision Points - Jan 24th.docx
Jan 24 2023 CCT Powerplan Naming and Specialty Prefix Decisions.docx
Order Sets by Clinical Area with Prioritization (New and Existing Combo) Jan 2023.xlsx
Pharmacy Engagement Tracker | Andrew will merge his physician stuff in here...
Physician Order Set Compare Tool
Temporary SaferCare Physician Order Website
High Priority Order Sets (Physician Feedback)
Complete List of CST Order Sets
CST Oncology Order Set List

## Additional Order Sets
CST Top Use - Anesthesia, etc
Check with pharm about order sets ready to go
Andrew will be taking these and putting them into the "Phase 1" tab
COPD Admission
COPD Discharge
Epoprostenol (Flolan) for Inhalation
already listed in phase 1 | Adult Ketamine Infusion/IM for Refractory Depression
Chemical Restraint
already listed in phase 1 | Clozapine Initiate Maintain & Monitor
already listed in phase 1 | Hypoglycemia Management
Orders for Newborn Infants
Adult Palliative Care Crisis Orders for Hospital Inpatients
Adult Palliative Care Orders For Hospital Inpatients
already listed in phase 1 | Asthma
already listed in phase 1 | Diabetes Management (Diabetic Ketoacidosis - DKA) - Admission
already listed in phase 1 | PED Acetaminophen (Tylenol) Overdose / NAC Admission (pending)
already listed in phase 1 | Seizures (Status EPI)
already listed in phase 1 | Sepsis (Rule Out) - Admission (Paediatrics) ( > 3 months)
Sepsis (Rule Out) - Admission (Paediatrics) (1-3 months)
Acute management of opiate/opioid withdrawal (subphase)
Alcohol withdrawal (adult) (subphase)
already listed in phase 1 | Buprenorphine/Naloxone (Suboxone) initiation for opiate withdrawal
Adult Detox Withdrawal
Nechako Youth Treatment Center
Benzodiazepine Withdrawal Orders
Aslo thinking of MED and OB | DVT/VTE Prophylaxis: Orthopedic Surgery Post Op (Adult) (Module)
Preoperative Hip Fracture
Pre-operative Orders
Preoperative Total Joint Replacement Orders
Preoperative Non-emergency Colon Resection Orders
?should we included some NIA/NIP to see how these plans work
SUBPHASES
Aminoglycosides/Gentamicin/Tobramycin & Therapeutic Drug Monitoring
Vancomycin & Therapeutic Drug Monitoring
Bowel Routine - Taking Opioid
Bowel Routine - Not Taking Opioid
Vaccines
Vaccinations Post-Emergent Splenectomy
SURG VTE Prophylaxis
OB VTE Prophylaxis
Buprenorphine-naloxone (maintenance)
First Priority
ED Shortness of Breath/Dyspnea
ED Allergic Reaction
ED Pain/Nausea/Vomiting
ED Opioid Overdose
ED Procedural Sedation (module)
ED Blood Body Fluid Exposure (BBFE)
ED Opioid Withdrawal
ED Cannabinoid Hyperemesis Syndrome
ED Alcohol Withdrawal Management
ED Vaginal Bleeding
ANES Epidural Intrathecal
ANES Postoperative
ANES Spinal
ANES Post-APS Sign-off Interim/Cover x 24 hours
ANES Preoperative Pediatric Sedation
AMB Iron Infusion
AMB PICC Line Insertion (Children and Adults)
AMB/ PAIN Subcutaneous Lidocaine Infusion for Pain
AMB/ PAIN Adult Ketamine IV Infusion for Chronic Refractory Pain
COVID-19 Palliative End of Life Care (with Joan)
COVID-19 Adult Palliative Care Orders (non-ICU) (with Joan)
COVID-19 Vaccine Orders LTC (with Joan)
COVID-19 Nirmatrelvir / ritonavir (Paxlovid) (with Joan)
ICU Electrolyte Replacement
ICU PEPuP Enteral Nutrition
ICU CRRT and CRRT Heparin
ICU Vasopressors/Inotropes
ICU Standard Ventilation
NEPH IPDN Orders (INTRADIALYTIC PN)
OB Elective/Planned (No Labour) Caesarean Section
OB FentaNYL for Pain Relief in Labour Clinical Protocol
OB Self Administered Medication (SAM) Program (CKHA) Version 1 or Version 2
OB Postpartum Orders: C-Section Delivery
OB Prevention of Mother to Infant Transmission of HIV Labour and Delivery
OB NIFEdipine Protocol Preterm Tocolysis
URO Preoperative Non-Emergency Major Urological Surgery
URO Postoperative Non-Emergency Major Urological Surgery
URO Day of Surgery Non-Emergency Major Urological Surgery
URO Post Percutaneous Nephrostomy Tube Insertion (with Joan)
NEO Nutrition Bloodwork
NEO Infant Parenteral Nutrition
PED Bronchiolitis (Jennifer Day reviewing)
PED Eating Disorders admission
PED Parenteral Nutrition
PED MH admission
PED Febrile Neutropenia
NEPH Chronic Hemodialysis
Request tool complete, attach once in priority list. Edit requests in inbox | NEPH Peritoneal Dialysis Peritonitis
NEPH Initial Renal Anemia Management Prescription
NEPH Alteplase Use for Occluded Hemodialysis Catheters
NEPH Hemodialysis Treatment
NH content reviewed recently | NEPH Insertion Tenckhoff Catheter
NH content reflects current practice | NEPH Chronic Peritoneal Dialysis (PD)
NEPH NxStage Home Hemodialysis
Request tool complete, attach once in priority list. Edit requests in inbox | NEPH Insertion Tenckhoff Catheter Nephrology Postoperative
NEPH New Patient Post Catheter Insertion Prescription
NEPH Bowel Care- Patients on Continuous Ambulatory Peritoneal Dialysis
SURG Postoperative Hip Fracture
SURG Same Day Joint Replacement Postoperative
SURG Post-Operative Hip and Knee Protocol (Day2)
SURG Postoperative Arthroscopy (Knee)
SURG Post-Operative Arthroscopy (Shoulder)
SURG Postoperative Total Joint Replacement
SURG Day of Surgery Non-emergency Colon Resection
SURG Preoperative Non-emergency Colon Resection
SURG Postoperative Non-emergency Colon Resection
SURG Leech Therapy
SURG Hospital at Home Postoperative
ONC BCG
SECOND PRIORITY
Hospital at Home Admission (HH Admission?)
Telemetry order set (with Joan)- word conversion completed
Cardiac Implantable Device Request form
CrCU/Cardiology/ED Amiodarone IV Infusion
ICU Transfer to Ward
ICU Palliative Care/End of Life Orders
ICU DCD-specific orders Donation after Circulatory Death
ICU Sedation Assessment/Spontaneous Breathing Trial/ICU Vent Weaning Clinical Protocol
OB Fallopian Tube Recanalization UHNBC
OB MAGnesium Sulfate for Preeclampsia (Seizure Prevention)
OB Bakri (Intrauterine) Balloon Monitoring
OB Stillbirth/Neonatal Death Investigations
OB RhIG (RhoGAM) for Rh-negative pts (Opt: Kleihauer-Betke)
OB VTE Prophylaxis: Labour & Delivery
OB VTE Prophylaxis: Labour & Delivery POSTPARTUM
OB Companion Well Baby
LTC Assessment-Service Approval (Form)
LTC Initiation of Antipsychotics for Dementia and BPSD
LTC Titration/Review of Antipsychotics for Dementia and BPSD
ENDO Continuous Subcutaneous Insulin Infusion - Insulin Pump
GI Morphine Enhanced Hepatobiliary Study
GI Post Liver Biopsy
ID Influenza (Oseltamivir) (Tamiflu) LTC
ID Intra-Abdominal Infections (IAI) (Antimicrobials)
ID Pneumonia VAP - Ventilator Associated (Antimicrobials)
ID Staph Aureus Bacteremia
MED Alteplase (Cathflo) for De-clotting Vascular Access
Inpatient Iron Infusion; Iron Deficiency Anemia Investigations & Treatment
MED Wound Care - Antimicrobial Management (Ulcers & Surface Wounds)
MED Wound Care - Pain Management and Odour Control (Ulcers & Palliative Wounds)
MED Wound Care - Supportive Management for Lower Extremity Wounds
MED Wound Care - Topical Ointments, Creams, Powders, and Liquids (Surface Management)
OPH Cataract and Intraocular Lens Implant Postoperative Orders
OPH Cataract Extraction and Intraocular Lens Implant Preoperative Orders
OPH Pre-Operative Cataract Drops Orders
NICU/PEDS OPH Eye exam
NEO Abstinence Syndrome (NAS) (Morphine, Phenobarb)
NEO Opioid Infusion (FentaNYL)
NEO Rapid Sequence Induction (RSI)
PAL Crisis Event: Community (Outpatient prescription)
PAL Community (Module) (outpatient prescription)
PED Diet - Regular (4 months-17 years)
PED Do Not Resuscitate
PED DIET Eating Disorder
PED Total Parenteral Nutrition (TPN) (< 1 year)
PED Total Parenteral Nutrition (TPN) (>10-18 years)
PED Total Parenteral Nutrition (TPN) (1 to 10 years)
PED Intravenous InFLIXimab Admission
NEPH Post Fistuloplasty of Hemodialysis Fistula/Graft move to diagnostics
NEPH Post Permcath Insertion
NEPH RiTUXimab Administration (use BCPRA resources)
SUS Safe supply (perinatal)
SUS iOAT continuation
SURG Fiberoptic Bronchoscopy
SURG Trans-Vaginal Tape and Trans-Obturator Tape Procedure Discharge
SURG Dentoalveolar/Orthognathic
SURG Day Care Discharge
Essential Cerner Model Recommendations Required for Certain Workflows
AP PowerPlans
Pathology Specimen Collection
Pathology Tissue Multipart Specimens
Breast Pathology Specimens
GI Pathology Specimens
GYN Oncology Pathology Specimens
Prostate Biopsy Pathology Specimens
Thoracic Pathology Specimens
Built by cerner | Blood Transfusion PowerPlans
Built by cerner | Blood Products: Emergent STAT
Built by cerner | Blood Products: Make Available and Transfuse
Note on B187: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Decide on naming

## HighPriority
[21 empty] | January | [6 empty] | February | [27 empty] | March
Index | Phase | Order Set | W | P | Type | CST Order Set | NH Order Set | Word file needed? | Word Conversion Completed? | NH content in date? | Comments | Stakeholders | DCW Author | Updated | DCW to Load | XML Author | Updated | XML to Load | Zynx Link | Builder | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5
1 | 1 | CARD Heart Failure |  |  | Module | DCW -- CARD Heart Failure with reduced ejection fraction (module) | Adult Heart Failure orders | Yes | Yes | N | NH contains flow chart |  | Jenn | 2023-02-27 | 🖬 |  |  |  |  | Joan TBA | Initial Build |  |  |  |  | Test |  | Engage | [11 empty] | Revise
2 | 1 | CARD STEMI Fibrinolytic Therapy |  |  | Module | DCW - CARD STEMI Fibrinolytic Therapy - Initial Management.xlsm | Andrew see email NH #10-111-5413 | No |  | yes | Suggest using NH content, CST workflow does not match paper order sets |  | Jess | 2023-02-27 | 🖬 |  |  |  |  | Joan TBA
3 | 1 | CARD STEMI Admission |  |  |  | DCW - CARD STEMI Post Fibrinolytic Therapy - Ongoing Management (Module).xlsm | Andrew see email NH #10-111-5414 | No |  | yes | Suggest using NH content, CST workflow does not match paper order sets |  | Jess | 2023-02-27 | 🖬 |  |  |  |  | Joan TBA
4 | 1 | CARD NSTEMI UA Admission |  |  |  | DCW - CARD NSTEMI and Unstable Angina - Ongoing Management (Module).xlsm | Andrew see email NH #10-111-5415 | No |  | yes | Suggest using NH content, CST workflow does not match paper order sets |  | Jess | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
5 | 1 | ED Chest Pain (Module) |  |  | Module | DCW - ED Chest Pain.xlsm | Draft NH #10-111-5412 | No |  | yes | DCW ED Chest Pain (not ischemia) better matches workflow, NH content doesn't worry about workflow. |  | Jenn | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
6 | 1 | MED Venous Thromboembolic (VTE) Treatment |  |  | Module | Zynx Deep Venous Thrombosis- Treatment- Module | Venous Thromboembolism Treatment Enoxaparin | Yes | Yes | no | updated Zynx content (deleted unneccesary info) there is a UHNBC outpt VTE treatment order set that has DOACs |  | Suzy | 2023-02-16 | 🖬 |  |  | TBA |  | Joan TBA
7 | 1 | ICU Sepsis |  |  | Module | DCW - General Sepsis (Adult).xlsm | Adult Sepsis Order Set | No |  | yes | ** recommend NH content as CST plan contains Sepsis Advisor -- currently being updated with working group |  | Jenn | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
8 | 1 | ICU Admission |  |  |  | DCW - ICU General Admission Medical Surgical.xlsm | Intensive Care Admission Orders | Yes | Yes | yes | Overall flow in CST could work but need to build the missing subphases/sections in the NH one. COnsult with ICU UHNBC as they made this draft and MMH/FSJ. |  | Jess | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
9 | 1 | COVID-19 Vaccination |  |  | Subphase | DCW - COVID-19 Vaccination (Module) CST-173077.xlsm | Adult Inpatient COVID-19 Vaccines Orders (ages 5 and up) | Yes | Yes | yes | Order set of convenience, would not consider high priority, use NH content not CST (can't find CST) |  | Jenn | 2023-02-28 | 🖬 |  |  | TBA |  | Joan TBA
10 | 1 | COVID-19 Remdesivir |  |  | Subphase | DCW - AMB COVID-19 remdesivir Treatment (Day of Treatment) CST-169933.xlsm | Remdesivir Infusion Orders (For COVID-19) | No |  | yes | Use NH content, workflow for COVID medications are specific to NH and may not be the same as CST/lower mainland. We also use this for both inpatient and AMB. |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
11 | 1 | COVID-19 General Admission |  |  |  | DCW - MED Covid19 Admission CST-173075.xlsm | COVID-19 Adult Admission Orders (non-ICU) | No |  | yes | Use NH content, similar to CST but will have some local nuances | Sharla / Med | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
12 | 1 | ED Asthma |  |  | Module | DCW - ED Asthma CST-73434.xlsm | CTAS Level 1 Asthma - Adult | Yes | Yes |  | Adult CTAS Level 2 or 3 Asthma Orders |  | Jenn | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
13 | 1 | RESP COPD Admission |  |  |  | DCW - Resp Chronic Obstructive Pulmonary Disease (COPD) exacerbationxlsm | COPD Exacerb. Admission Orders | No |  | New content in word file with JennD | COPD Exacerb. 48hr after Admission Orders; these are with Sharla to approve updates |  | Jenn | 2023-02-16 | 🖬 |  |  | TBA |  | Joan TBA
14 | 1 | GERI MED Delirium |  |  | Module | DCW - Delirium (Geriatrics_Adult) (Module).xlsm | Elderly Delirium Orders | Yes | Yes | no | NH is site specific |  | Suzy | 2023-02-24 | 🖬 |  |  | TBA |  | Joan TBA
15 | 1 | ICU Diabetic Ketoacidosis (DKA) / Hyperglycemic Hyperosmolar State (HHS) |  |  |  | DCW - DCW - ED Diabetic Ketoacidosis (DKA) - Adults 19 Years and Older.xlsm | Adult Orders for Diabetic Ketoacidosis (DKA)/Hyperglycemic Hyperosmolar State (HHS) | Yes | Yes | no | *NH working group paused; Andrew sent CST DCW to Beth Ann on Feb 16, 2023 |  | Andrew D | 2023-02-16 | 🖬 |  |  | TBA |  | Joan TBA
16 | 1 | ED Seizure |  |  | Module | DCW - ED Seizure - CST 119320.xlsm | NA | No |  |  |  |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
17 | 1 | MED Admission |  |  | Module | DCW - MED General Medicine Admission.xlsm | Medical Patient Admission Orders | Yes | Yes | yes |  |  | Suzy | 2023-02-24 | 🖬 |  |  | TBA |  | Joan TBA
18 | 1 | DIET Enteral Nutrition |  |  | Module | DCW - Enteral Tube Feeding - Initiation (Module) | Enteral Nutrition | No |  | yes | neither CST or NH is only unblocking feed tube |  | Suzy | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
19 | 1 | ED Code Trauma |  |  | Module | DCW - ED Trauma CST-57910.xlsm | Code Trauma Initial Orders | Yes | Yes | yes |  |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
20 | 1 | PED ED Asthma Acute Management |  |  | Module | DCW - ED PED Asthma (wt greater than 20kg) | Pediatric Asthma Emergency Management | No |  | yes |  |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
21 | 1 | ED Sexual Assault |  |  | Module | DCW - ED Sexual Assault.xlsm | Sexual Assault Physician's Orders | No |  | yes |  |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
22 | 1 | PED ED Code Trauma |  |  | Module | DCW - PED ED Trauma CST-57910.xlsm | Pediatric Code Trauma | Yes | Yes | yes | ?adult trauma linked |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
23 | 1 | ID Meningitis |  |  | Module | DCW - ED Meningitis CST-37702.xlsm | No current NH content but AMS creating | No |  |  | would likely want this NOT ED specific but gen med module (AMS has content) |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
24 | 1 | ID Pneumonia CAP (Community-Acquired) |  |  | Module |  | Community Acquired Pneumonia | Yes | Yes | yes | please use NH content (ABX are different) |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
25 | 1 | ID Pneumonia HAP (Nosocomial/Hospital-Acquired) |  |  | Module | DCW - MED Hospital Acquired Pneumonia Management - CST-173072.xlsm | No current NH content but AMS/CC creating | No |  |  | AMS has created content |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
26 | 1 | NEURO Stroke Ischemic WITH tPA |  |  | Module | DCW - ED NEURO Ischemic Stroke Reperfusion Treatment CST-173062.xlsm | Thrombolytic Therapy for Stroke | yes | Yes | no | Being updated currently JD |  | Jenn | wrong file | 🖬 |  |  | TBA |  | Joan TBA
27 | 1 | NEURO Stroke Ischemic without tPA Admission |  |  |  | DCW - Ischemic Stroke – Without Reperfusion admission CST-173063.xlsm | Ischemic Stroke - Initial 24 Hours Post Thrombolysis Order Set | yes | Yes | yes | Ischemic Stroke - Greater than 24 Hours Post Thrombolysis Order Set |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
28 | 1 | NEURO Transient Ischemic Attack (TIA) Admission |  |  |  | DCW - NEURO Stroke Management CST-171233.xlsm | Acute Stroke - Non Thrombolysis and Transient Ischemic Attack (TIA) Admission Order Set | yes | Yes | yes | see NH for admission order vs CST ED to outpatient |  | Jenn | wrong file | 🖬 |  |  | TBA |  | Joan TBA
29 | 1 | SURG General Admission |  |  |  | DCW - GENSURG General Surgery Admission.xlsm | No NH content | no |  | no | Erin Martin created draft, contains ABX |  | Suzy | 2023-02-27 | 🖬 |  |  | TBA |  | Joan TBA
30 | 1 | NEURO Hemorrhagic Stroke (ICH) Admission |  |  |  | DCW - NEURO Stroke Admission Primary Intracerebral Hemorrhage CST-173067.xlsm | No NH content | No |  | no |  |  | Jenn | 2023-03-06 | 🖬 |  |  | TBA |  | Joan TBA
31 | 1 | AMB Penicillin Graded Challenge |  |  |  | DCW - AMB Penicillin Challenge (Day of Treatment) CST-104714.xlsm | UHNBC NH content awaiting CAT | no |  | yes |  |  | Jenn | 2023-03-07 | 🖬 |  |  | TBA |  | Joan TBA
32 | 1 | ICU Diabetic Ketoacidosis |  |  |  | DCW - Diabetic Ketoacidosis (DKA) Adult 19 Years and Older - Initial to Management.xlsm | No NH admission specific order set | no |  | no | (Build on Hold - Being rebuilt with DKA Working Group) |  | Jenn | 2023-03-07 | 🖬 |  |  | TBA |  | Joan TBA
33 | 1 | PED ED Acetaminophen (Tylenol) Overdose / NAC |  |  |  | DCW - PED Acetylcysteine for Acetaminophen Poisoning Admission.xlsm | NH content in stakeholding | no |  | yes- will be | Adult content also in stakeholding |  | Jenn | 2023-03-07 | 🖬 |  |  | TBA |  | Joan TBA
34 | 1 | ENDO Subcutaneous Insulin Orders (Basal/Prandial/Sliding Scale/NPO) |  |  |  | DCW - Insulin+Subcutaneous for Patients Eating or NPO (Sliding+Scale)+(Module) | UHNBC insulin sliding scale | no |  | yes- will be | Do not use insulin regular. UHNBC BBIT order set with working group. |  | Jenn | 2023-03-07 | 🖬 |  |  | TBA |  | Joan TBA
35 | 1 | MED Eating Disorders Medical Stabilization Admission |  |  | Module | DCW - MED Eating Disorders (Module) CST-43851.xlsm | Adult Eating Disorders Medical Stabilization Orders for Inpatient Admissions | Yes | Yes | yes |  |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
36 | 1 | PED Sepsis Age 29 Days and Greater |  |  | Module | DCW - PED Sepsis for Age Greater Than 28 Days Admission.xlsm | Ped sepsis 29 days and greater | no |  | yes |  |  | Jenn | 2023-03-07 | 🖬 |  |  | TBA |  | Joan TBA
37 | 1 | MED VTE Prophylaxis |  |  | Subphase | DCW - VTE prophlyaxis medicine (module) | Adult VTE prophylaxis in acute care patients | yes | Yes | no | More VTE prophylaxis in CST Horizontal DCW |  | Suzy | 2023-02-28 | 🖬 |  |  | TBA |  | Joan TBA
38 | 1 | SUS Acute Management of Opioid Withdrawal |  |  | Module | DCW - ED Opioid Withdrawal.xlsm | NH content imbedded in Suboxone orders | Yes -- pull from 10-111-5095 |  | no | NH content imbedded in Suboxone orders |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
39 | 1 | SUS Alcohol Withdrawal |  |  | Module | DCW - Alcohol withdrawal Management (CIWA) (Module) - CST-124007 | NH content updated but not released yet, need to build the NH content as recently agreed upon. | [5 empty] | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
40 | 1 | SUS Buprenorphine/Naloxone (Suboxone) Initiation for Opiate Withdrawal (Module) |  |  |  | DCW - Buprenorphine-Naloxone (Suboxone) induction (Module) CST-124010.xlsm | Suboxone standard induction orders | yes | Yes | no |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
41 | 1 | DIET Total Parenteral Nutrition (TPN) (Module) |  |  | Module | DCW - Parenteral Nutrition (PN - TPN) Initiation (Multiphase) CST-96749.xlsm | Parenteral Nutrition Orders 3-in-1 Solution - Adult | no |  | yes | consider keeping as a paper order set but initiate order electronically? |  | Suzy |  | 🖬 |  |  | TBA |  | Joan TBA
42 | 1 | MH Psychiatric Admission |  |  |  | DCW - MH Psychiatric Admission CST-45637 and CST-58173.xlsm | Adult (19 plus) Psychiatry Admission Orders | no |  | yes |  |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
43 | 1 | MED PICC Line Insertion |  |  | Module | DCW Peripherally Inserted Central Catheter Insertion (PICC) - Inpatient.xlsm | PICC line insertion adults and children | yes | Yes | no |  |  | Suzy | 2023-02-28 | 🖬 |  |  | TBA |  | Joan TBA
44 | 1 | AMB ID IV Antimicrobial Therapy |  |  | Module | DCW - ED Long Term Antibiotic Therapy (qweekly) (RUR) (Day of Treatment).xlsm | Outpatient IV antimicrobial therapy | no |  | yes | Can we use ABX from NH content please? |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
45 | 1 | ICU ARDS Ventilation Protocol (Module) |  |  | Module | Use NH content please | Mechanical Ventilation in Patients with Acute Respiratory Distress (ARDS) Regional | yes | Yes but not well - needs CPS for 80% content | no |  |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
46 | 1 | ICU Sedation and Analgesia (Subphase) |  |  | Subphase | Use NH content please | Intensive Care Sedation and Analgesia Orders | no |  | no | AndrewD: I did a dirty conversion of the NH PDF |  | Jess |  | 🖬 |  |  | TBA |  | Joan TBA
47 | 1 | Nicotine Replacement |  |  | Subphase | Use NH content please | Nicotine withdrawal protocol | yes | Yes | no | Andrew will edit with NH Content (Mar 6/23); Can only find PEDS in CST; maybe we should have a peds and adult too? JD |  | Jenn |  | 🖬 |  |  | TBA |  | Joan TBA
48 | 1 | MED Wound Care - Negative Pressure Wound Care Therapy/VACD (Module) |  |  |  | DCW - Negative Pressure Wound Therapy (VAC) (Module).xlsm | Negative pressure wound therapy | no |  | no |  |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
49 | 1 | ENDO Hypoglycemia Management (Module) |  |  |  | DCW - ED METABOLIC Management of Hypoglycemia (Module) CST-171208.xlsm | Management of hypoglycemia in diabetes | yes | Yes | no |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
50 | 1 | ID Cellulitis /SSTI (Module) |  |  |  | DCW - Med Cellulitis (module) | No current NH content but AMS creating | no |  |  | NH content complete |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
51 | 1 | NIA Urinary Retention (Module) |  |  |  | DCW - ADULT PED NIA Urinary Retention | No NH content | no |  |  | pulled NIA content to see how build goes |  | Suzy | 2023-03-01 | 🖬 |  |  | TBA |  | Joan TBA
52 | 1 | ID Febrile Neutropenia (Module) |  |  |  | DCW - ED Febrile Neutropenia.xlsx | Adult Febrile Neutropenia | no |  | yes | Andrew Updated Teams Link Mar 6/23 |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
53 | 1 | ID Pyelonephritis (Module) |  |  |  | DCW - Med urinary tract infection (UTI) pyelonephritis (module) | No current NH content but AMS creating | no |  |  | NH content underway |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
54 | 1 | GI H. Pylori Eradication (Module) |  |  |  | DCW - GI Helicobacter Pylori Treatment Regimens CST-41092.xlsm | No current NH content | no |  |  |  |  | Suzy | 2023-03-01 | 🖬 |  |  | TBA |  | Joan TBA
55 | 1 | ED Major Burn - Initial 24 Hours Fluid Resuscitation Orders for Adults (Module) |  |  |  | 435 DCW - ED Major Burns CST-39691.xlsm | Major burns -- Initial 24 hours fluid resusitation | yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
56 | 1 | ED Headache (module) |  |  |  | DCW - ED Headache- CST 190569.xlsm | Adult migraine orders | no |  |  |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
57 | 1 | OPH Photodynamic Therapy Treatment (Module) |  |  |  | DCW - OPHTH AMB Angiography (FA-ICG) and Photodynamic Laser Therapy (Day of Treatment).xlsm | Photodynamic treatment orders | no |  | no | has a Nurse Initiated post-procedure phase in this CST plan |  | Suzy | 2023-03-01 | 🖬 |  |  | TBA |  | Joan TBA
58 | 1 | URO Extracorporeal Shock Wave Lithotripsy (Module) |  |  |  | DCW - UROL Extracorporeal Shockwave Lithotripsy (ESWL) (Multiphase) - CST-38311.xlsm | Extracorporeal Shockwave Lithotripsy | no |  | no | Also has a Nurse Initiate Pre-Procedure order |  | Suzy | 2023-03-01 | 🖬 |  |  | TBA |  | Joan TBA
59 | 1 | OB MAGnesium Sulfate for Fetal Neuroprotection (Subphase) |  |  |  | DCW - OB Magnesium Sulfate Administration for Fetal Neuroprotection (Module) CST-105122.xlsm | Mg orders imbedded in Hypertensive disorders in pregnancy orders (intrapartum, antepartum, postpartum) | Yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
60 | 1 | GI Bowel Preparation (Module) |  |  |  | DCW - GI Bowel Preparation - Inpatient CST-77707 | No current NH content | no |  |  |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
61 | 1 | MH Adult Ketamine Infusion/IM for Refractory Depression (Module) |  |  |  | DCW - MH Psychiatry Ketamine Infusion for Refractory Depression - CST-35519.xlsm | NH regional in progress | no |  |  |  |  | Jess | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
62 | 1 | OB Postpartum Hemorrhage (Subphase) |  |  |  | DCW - OB Postpartum Hemorrhage (Module).xlsm | Orders imbedded in Post Partum orders | yes | Yes | yes | Mat SNL (Vanessa) would like to updated content |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
63 | 1 | OB Postpartum Hypertension (Module) |  |  |  | DCW - OB Gestational Hypertension and Pre-Eclampsia Postpartum (Module).xlsm | Hypertensive Disorders in Pregnancy: Postpartum Orders | yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
64 | 1 | OB Oxytocin Induction or Augmentation Of Labour (Module) |  |  |  | DCW - OB Induction or Augmentation of Labour with Oxytocin (Module).xlsm | Oxytocin Induction/ Augmentation of Labour | yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬 |  |  | TBA |  | Joan TBA
65 | 1 | MH Clozapine Maintenance (Module) |  |  |  | DCW - MH cloZAPine Maintenance (Module) CST-56230.xlsm | Clozapine Adult Inpatient Orders | No |  | yes | CST has separate order for initiate/titrate, maintenance and monitor. NH only uses Genpharm/Mylan to initiate. NH build an initiation slow, initiation moderate and maintenance (no separate monitor for now) |  | Suzy | 2023-03-03 | 🖬 |  |  | TBA |  | Joan TBA
66 | 1 | MH Clozapine Initiation (Module) |  |  |  | DCW- MH cloZAPine (GENPHARM or MYLAN)(Custon daily)(Module) | Clozapine Adult Inpatient Orders | No |  | yes | Please note: 2 builds in MUM 1st review- slow and moderate. I attemped to combine CST content so may be a messy translation |  | Suzy | 2023-03-03 | 🖬
67 | 1 | PED Admission |  |  |  | DCW - PED General Admission.xlsm | No NH content | [5 empty] | Suzy | 2023-03-06 | 🖬
68 | 1 | NICU Admission |  |  |  | DCW - NICU Inborn Admission CST-107321.xlsm | NICU Newborn Infant Orders | no |  | no | I am not sure about these-NH is bare bones but depends on application |  | Suzy | 2023-03-06 | 🖬
69 | 1 | LTC Admission |  |  |  | N/A - Andrew D built a rough draft based on NH PDF | Long Term Care Facilities Admission Orders | no |  | yes | NH OS currently being updated in final stakeholding stage JD; AndrewD roughly converted the current NH order set into a |  | Jenn | awaiting new content | 🖬
70 | 1 | ANES Postpartum Intrathecal Epidural Opioid |  |  |  | DCW - ANES Postpartum Intrathecal Epidural Opioid.xlsm | No NH content | no |  | no | NH content for case room (labour epidural) that is site specific. |  | Suzy | 2023-03-06 | 🖬
71 | 1 | ANES Epidrual Analgesia |  |  |  | DCW - ANES Epidural Analgesia CST-174603.xlsm | Analgesia Orders | yes | Yes | no | NH has regional OS and UHNBC pain clinic OS |  | Suzy | 2023-03-08 | 🖬
72 | 1 | ANES PCA |  |  |  | DCW - ANES Patient Controlled Analgesia (PCA) (Module).xlsm | BVDH Patient Controlled Analgesia (PCA) orders | yes |  | no | NH has no regional orders but content very similar between NH OS |  | Suzy | 2023-03-06 | 🖬
73 | 1 | CARD Transesophageal Echocardiogram (TEE) |  |  |  | DCW - CARD Transesophageal Echocardiogram (TEE) Post Procedure - CST - 37901.xlsm | No NH content | no |  |  |  |  | Suzy | 2023-03-07 | 🖬
74 | 1 | COVID-19 Baricitinib |  |  | Subphase | DCW - ICU HAU COVID -19 tocilizumab or baricitinib Treatment (Module).xlsm | Baricitinib (For COVID-19 Only) | no |  | yes | Use NH content; workflow for COVID medications are specific to NH and may not be the same as CST/lower mainland. |  | Jess | 2023-03-06 | 🖬
75 | 1 | COVID-19 ICU Admission |  |  |  | DCW - MED Covid19 Admission CST-173075.xlsm | Intensive Care Admission Orders (for COVID-19 only) | no | Yes | yes | Use NH content; There is a word conversion of NH paper order set completed for DCW build |  | Jess | 2023-03-06 | 🖬
76 | 1 | COVID-19 Tocilizumab |  |  | Subphase | DCW - ICU HAU COVID -19 tocilizumab or baricitinib Treatment (Module).xlsm | Tocilizumab Infusion Orders: Critically Ill (For COVID-19 Only) | no |  | yes | Use NH content; workflow for COVID medications are specific to NH and may not be the same as CST/lower mainland. |  | Jess | 2023-03-06 | 🖬
77 | 1 | COVID-19 Sotrovimab |  |  | Subphase | DCW - Sotrovimab infusion for COVID-19 (Inpatient) CST-156919.xlsm | Sotrovimab Infusion Orders (For COVID-19 Only) | no |  | yes | Use NH content; workflow for COVID medications are specific to NH and may not be the same as CST/lower mainland. For inpatient and outpatient |  | Jess | 2023-03-06 | 🖬
78 | 1 | ICU Hyperkalemia |  |  |  | DCW - ED Hyperkalemia Management.xlsm | No NH content | no |  |  |  |  | Jenn | 2023-03-08 | 🖬
79 | 1 | ICU IV Insulin Infusion |  |  | Module | DCW - Insulin Infusion (Module) - CST - 130855.xlsm | Insulin Infusion (ICU Only) | no |  | no |  |  | Jess | 2023-03-06 | 🖬
80 | 1 | ICU Hypertonic Saline 3% Sodium Chloride for Hyponatremia with Severe Symptoms |  |  |  | DCW - ED Electrolyte Replacement Module CST-39731.xlsm | No NH content | no |  |  | Andrew - link has the title of ICU hypertonic saline vs elec replacement |  | Jess | 2023-03-06 | 🖬
81 | 1 | DIET Enteral Nutrition and Feeding Tube Management |  |  |  | DCW - AMB Enteral Tube Feeding (Multiphase).xlsm | Adult Enteral Nutrition Orders | no |  | yes | NH OS same as B20 with all components in one OS |  | Suzy |  | 🖬
82 | 1 | LTC Diet |  |  |  | N/A - Andrew D built a rough draft based on NH PDF | Long Term Care Admission Orders: Diet Order | no |  | no |  |  | Suzy | 2023-03-07 | 🖬
83 | 1 | ED Spine Management |  |  |  | DCW - TRAUMA Spine Precautions Management (Module) CST-45381.xlsm | Spine Management Orders | [5 empty] | Jenn | 2023-03-08 | 🖬
84 | 1 | OB Antepartum Hemorrhage Admission and Management |  |  |  | No CST Content | No NH content |  |  |  | Updated Mar 8/23: Andrew D built a simple DCW from NYGH; Note: this is the WRONG CST order set, put here as a template; NH content in development? AndrewD - Yep! (Mar6/23) |  | Jenn | needs clean up in zynx | 🖬
85 | 1 | OB Fetal Loss |  |  |  | DCW - OB Fetal Demise and or Loss Greater than 13 Weeks (Multiphase).xlsm | No NH content | [5 empty] | Jenn | 2023-03-08 | 🖬
86 | 1 | OB Placenta Previa / PPROM / Preterm Labour Admission |  |  |  | DCW - OB Preterm Premature Rupture of Membranes (PPROM) (Module) CST-131994.xlsm | PPROM- Admission (less than 36+6 weeks) | no |  | yes | No NH content for Placenta Previa |  | Jenn | 2023-03-08 | 🖬
87 | 1 | OB Vaginal Delivery (non-Diabetic Patient) |  |  |  | DCW - OB Postpartum Vaginal Delivery CST-132030.xlsm | Intrapartum Admission Orders | yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬
88 | 1 | OB Postpartum Orders: Vaginal Delivery |  |  |  | DCW - OB Postpartum Vaginal Delivery (Assisted Vaginal Birth or Complex Lacerations) (Multiphase) CST-161975.xlsm | Postpartum Orders | yes | Yes | yes |  |  | Jenn | 2023-03-08 | 🖬
89 | 1 | MED Heparin Induced Thrombocytopenia (HIT) |  |  |  |  | No NH content |  |  |  | Andrew Updated with TSSO Content Mar 8 2023 |  | Jess | 2023-03-08 | 🖬
90 | 1 | GI Cirrhosis/Encephalopathy/Ascites/Bacterial Peritonitis |  |  |  | DCW - GI Cirrhosis New Diagnosis Investigations (Module).xlsm | Decompensated Cirrhosis Orders | yes | Yes | no | This is only investigations/lab = a lab powerplan? We will likley need to re-vamp and make a NH one specific to the cirrhosis piece. SBP would possibly land with GI and ID. |  | Jess | 2023-03-08 | 🖬
91 | 1 | GI Alcoholic Hepatitis |  |  |  | DCW - Managed Alcohol (Module) CST-39140.xlsm | No NH content |  |  |  | AndrewD - Used NYGH Content - updated Mar 8 2023 |  | Jess | 2023-03-08 | 🖬
92 | 1 | ID Aspiration Pneumonia |  |  |  | DCW - Med Pneumonia -CST-173070.xlsm | NH Content created with AMS | no |  |  | No CST content, use NH Firstline recommendations available |  | Jenn | 2023-03-08 | 🖬
93 | 1 | ID C. Difficile Infection |  |  |  | DCW - PED Clostridioides difficile (C. difficile) Treatment (Module) CST-107761.xlsm | Clostridium Difficile Infection (CDI) Treatment for Adult Inpatient Orders | no, done by JD |  | yes | No CST content, Use NH content; CST used as placeholder; NH word file created and with HLS for DCW creation JD |  | Jenn | 2023-03-08 | 🖬
94 | 1 | MED Wound Care - Advanced Treatments (Cavities & Surface Wounds) |  |  |  | Use TSSO Content | No NH content |  |  |  | Andrew D used TSSO Content |  | Jess | 2023-03-08 | 🖬
95 | 1 | MED Wound Care - Topical & Packing Treatments (Tunneled Wounds, Cavities & Surface Wounds) |  |  |  | Use TSSO Content | No NH content |  |  |  | Andrew D used TSSO Content |  | Jess | 2023-03-08 | 🖬
96 | 1 | OPH Cataract and Trabeculectomy |  |  |  | DCW - OPHTH Ophthamology Pre Operative (Day of Surgery).xlsm | Cataract and Trabeculectomy Orders | yes | Yes | yes |  |  | Jess | 2023-03-08 | 🖬
97 | 1 | PAIN Fentanyl Transdermal Patch |  |  | Subphase | DCW - ANES Labour Fentanyl Patient Controlled Analgesia (PCA) (Module).xlsm | Fentanyl Transdermal Patch | no, done by SS (HLS) | yes | no | CST used as placeholder, built in Zynx |  | Suzy | NA | 🖬
98 | 1 | URO Postoperative Transurethral Prostatic Resection and Bladder Tumours |  |  |  | DCW - UROL Transurethral Resection of Prostate (TURP) Post Operative (Multiphase) - CST-70466.xlsm | Postoperative Transurethral Prostatic Resection (TURP) and Bladder Tumours (TURBT) | yes | Yes | yes | Build in Zynx |  | Jess | 2023-03-08 | 🖬
99 | 1 | URO Cystoscopy |  |  | Multiphase and Documentation |  | Cystoscopy Orders and Record | yes | Yes | no | site sp to UHNBC, MMH, BVDH; AndrewD converted NH orders |  | Jess | 2023-03-08 | 🖬
100 | 1 | RESP Thoracentesis |  |  |  | DCW - RESP AMB Thoracentesis and Thoracentesis Drainage (Multiphase).xlsm | No NH content | n/a |  | n/a | NIP pre and post procedure |  | Suzy | 2023-03-08 | 🖬
101 | 1 | NEPH Potassium Dialysate Management |  |  |  | DCW - NEPH Peritoneal Dialysis (PD).xlsm | Potassium Dialysiate Management Orders for Chronic Hemodialysis Patients | no, done by SS (HLS) | yes | no | word file for DCW built |  | Suzy | NA | 🖬
102 | 1 | NEPH Hemodialysis Warfarin Outpatient |  |  |  | DCW - NEPH Warfarin Protocol for Hemodialysis (Module).xlsm | Hemodialysis Warfarin Outpatient Orders (for UHNBC dialysis unit. CDUs need approval from nephrologist) | yes, done by SS (see floppy disc) | yes | no |  |  | Suzy | 2023-03-09 | 🖬
103 | 1 | SUS Methadone Initiation / Continuation |  |  |  | DCW - SUS Methadone for Opioid Use Disorder CST-44989.xlsm | No NH content | n/a |  | n/a |  |  | Jenn | 2023-03-08 | 🖬
104 | 1 | SURG Thoracic Preop (Day of Surgery) |  |  |  | DCW - TSURG Pre Operative (Day of Surgery).xlsm | No NH content | n/a |  | n/a | renamed as SURG Thoracic Preop (Day of Surgery) since there are many different preop and postop that can be built |  | Suzy | 2023-03-09 | 🖬
105 | 1 | SURG Thoracic Postop (Multiphase) |  |  |  | DCW - TSURG General - Post Operative (Multiphase).xlsm | No NH content | n/a |  | n/a | renamed as SURG Thoracic Postop to indicate surgery type |  | Suzy | 2023-03-09 | 🖬
106 | 2 | Pathology Specimen Collection |  |  |  | DCW - PED RESP Pathology Specimen (Module).xlsm | Poor match - Cerner standard order?
107 | 2 | Pathology Tissue Multipart Specimens |  |  |  | (CareOrders doesn't do lab ones - if no medications; Thomas & Debby, Tammy)
108 | 2 | Breast Pathology Specimens
109 | 2 | GI Pathology Specimens
110 | 2 | GYN Oncology Pathology Specimens
111 | 2 | Prostate Biopsy Pathology Specimens
112 | 2 | Thoracic Pathology Specimens
113 | 2 | Blood Transfusion PowerPlans
114 | 2 | Blood Products: Emergent STAT
115 | 2 | Blood Products: Make Available and Transfuse
106 | 2 | ED Shortness of Breath/Dyspnea |  |  |  | DCW - ED Shortness of Breath Dyspnea.xlsm
107 | 2 | ED Allergic Reaction |  |  |  | DCW - ED Allergic Reaction CST-39615.xlsm
108 | 2 | ED Pain/Nausea/Vomiting |  |  |  | DCW - ED Pain Nausea Vomiting (Module).xlsm
109 | 2 | ED Opioid Overdose
110 | 2 | ED Procedural Sedation (module) |  |  |  | DCW - ED Procedural Sedation (Module) CST-99679.xlsm
111 | 2 | ED Blood Body Fluid Exposure (BBFE) |  |  |  | DCW - ED Blood Body Fluid Exposure (BBFE) .xlsm
112 | 2 | ED Cannabinoid Hyperemesis Syndrome |  |  |  | DCW - SUS Cannabinoid Hyperemesis Syndrome - CST-140526.xlsm
113 | 2 | ED Alcohol Withdrawal Management |  |  |  | DCW - Alcohol withdrawal Management (CIWA) (Module) - CST-124007.xlsm | NH content as above | no |  | yes
114 | 2 | ED Vaginal Bleeding |  |  |  | DCW - ED Vaginal Bleeding CST-40027.xlsm
115 | 2 | COPD Admission |  |  |  |  | NH content as above | no |  | yes
116 | 2 | COPD Discharge |  |  |  |  | NH content as above | no |  | yes
117 | 2 | RESP Epoprostenol (Caripul) for Inhalation |  |  |  | RESP Prostacyclin Administration (Module) | Inhaled Epoprostenol (Caripul ONLY) orders | Yes | Yes | yes
118 | 2 | Chemical Restraint |  |  |  |  | No NH content
119 | 2 | Orders for Newborn Infants |  |  |  | DCW - PED Newborn Admission.xlsm | Currently being updated JD | No |  | being updated JD
120 | 2 | Adult Palliative Care Crisis Orders for Hospital Inpatients |  |  |  |  | Adult Palliative Care Crisis Event orders | Yes | Yes | yes
121 | 2 | Adult Palliative Care Orders For Hospital Inpatients |  |  |  | DCW - PAL Palliative Sedation Therapy.xlsm | Adult Palliative Care Orders for Hospital Inpatients | Yes | Yes | yes
122 | 2 | Sepsis (Rule Out) - Admission (Paediatrics) (1-3 months) |  |  |  |  | Pediatric Sepsis 0 days of age to 28 days of age | No |  | Yes
123 | 2 | Acute management of opiate/opioid withdrawal (subphase) |  |  |  |  | NH content as above | no |  | yes
124 | 2 | Alcohol withdrawal (adult) (subphase) |  |  |  |  | NH content as above | no |  | yes
125 | 2 | Adult Detox Withdrawal
126 | 2 | Nechako Youth Treatment Center |  |  |  |  | Youth General Admission Orders | no |  | yes
127 | 2 | Benzodiazepine Withdrawal Orders |  |  |  |  | NH content being developed JD | NH content being developed JD
128 | 2 | DVT/VTE Prophylaxis: Orthopedic Surgery Post Op (Adult) (Module) |  |  |  |  | VTE prophylaxis post Hip and Knee arthroplasty | yes | Yes | no
129 | 2 | ORTHO Preoperative Hip Fracture |  |  |  | DCW - ORTHO Fractured Hip Pre-Operative Orders (Regional).xlsm | need regional order set
130 | 2 | ORTHO Postoperative Hip Fracture |  |  |  | DCW ORTHO Fractured Hip- Post Operative (Regional) (Multiphase) | need regional order set
131 | 2 | SURG Preoperative Orders |  |  |  | DCW GENSURG Surgical Inpatient Preparation (Module) | need regional order set
132 | 2 | SURG Postoperative Orders |  |  |  | DCW GENSURG General- Post Operative (Multiphase) | need regional order set
133 | 2 | ICU Electrolyte Replacement |  |  |  |  | ICU electrolyte replacement orders | yes | Yes | no
134 | 2 | ICU PEPuP Enteral Nutrition |  |  |  |  | Critical Care Adult PEPuP Enteral Nutrition Orders | yes |  | yes
135 | 2 | ICU CRRT |  |  |  |  | CRRT orders | yes | Yes | no
136 | 2 | ICU CRRT Heparin |  |  |  |  | CRRT heparin orders | yes |  | no
136 | 2 | ICU Vasopressors/Inotropes |  |  |  |  | Vasopressor and inotrope orders | yes | Yes | no
137 | 2 | ICU Standard Ventilation
138 | 2 | ICU Transfer to Ward |  |  |  |  | Intensive Care transfer to wards | Yes | Yes | no
139 | 2 | ICU Palliative Care/End of Life Orders |  |  |  |  | Intensive Care Comfort Care-Palliative order | Yes | Yes | no
140 | 2 | ICU DCD-specific orders Donation after Circulatory Death
141 | 2 | ICU Sedation Assessment/Spontaneous Breathing Trial/ICU Vent Weaning Clinical Protocol
142 | 2 | ID Influenza (Oseltamivir) (Tamiflu) LTC |  |  |  |  | Oseltamivir for influenza outbreak declared | Yes | Yes | no
143 | 2 | ID Intra-Abdominal Infections (IAI) (Antimicrobials) |  |  |  |  | Will create content with AMS
144 | 2 | ID Pneumonia VAP - Ventilator Associated (Antimicrobials) |  |  |  |  | Creating content with CRIT and AMS
145 | 2 | ID Staph Aureus Bacteremia |  |  |  |  | Word file with JD | No |  | yes
146 | 2 | ANES Epidural Intrathecal |  |  |  | DCW - ANES Epidural Analgesia CST-174603.xlsm | need regional order set | TBD |  | no
147 | 2 | ANES Postoperative (?general for all surgeries) |  |  |  |  | need regional order set
148 | 2 | ANES Spinal |  |  |  | ANES Epidural Analgesia | need regional order set
149 | 2 | ANES Post-APS Sign-off Interim/Cover x 24 hours |  |  |  | ANES Multi-Modal Pain Management
150 | 2 | ANES Preoperative Pediatric Sedation |  |  |  | No CST content | need regional order set | TBD |  | no
151 | 2 | AMB Iron Infusion (sucrose) |  |  |  | DCW AMB Iron Sucrose Infusion qdaily for 2 days (Day of Treatment) | Outpatient Adult IV Iron Sucrose orders | yes | Yes | no
152 | 2 | AMB PICC Line Insertion (Children and Adults) |  |  |  | AMB Peripherally Inserted Central Catheter Insertion (PICC) (Multiphase) | PICC in children and adults | Yes | Yes | no
153 | 2 | AMB/ PAIN Subcutaneous Lidocaine Infusion for Pain |  |  |  | DCW - AMB Lidocaine Infusion for Chronic Pain - Initial Treatment (Day of Treatment).xlsx | Subcutaneous Lidocaine Infusion for pain | yes | Yes | yes
154 | 2 | AMB/ PAIN Adult Ketamine IV Infusion for Chronic Refractory Pain |  |  |  | DCW - ANES AMB Ketamine Infusion for Chronic Pain (Day of Treatment).xlsm | Adult Ketamine IV infusion orders for Chronic Refractory Neuropathic pain | yes | Yes | yes
155 | 2 | CRIT COVID-19 Palliative End of Life Care |  |  |  | no content | COVID-19 Palliative Sedation and end of life orders | yes | Yes | no
156 | 2 | COVID-19 Adult Palliative Care Orders (non-ICU) |  |  |  | PAL COVID-19 End of Life- Terminal Care Orders | COVID-19 Palliative End of life (non-ICU) | no |  | no
157 | 2 | COVID-19 Vaccine Orders LTC |  |  |  | No orders | LTC COVID-19 Primary Series Vaccine order | no |  | yes
158 | 2 | COVID-19 Nirmatrelvir / ritonavir (Paxlovid) |  |  |  | COVID-19 Treatments | Nirmetrelvir-Ritonavir (Paxlovid) orders for COVID-19 | no |  | yes
159 | 2 | NEPH IDPN Orders (INTRADIALYTIC PN) |  |  |  | NEPH AMB Intradialytic Parenteral Nutrition qweekly for 3 months (day of treatment) | Intradialytic Parenteral Nutrition orders | yes |  | yes
160 | 2 | OB Elective/Planned (No Labour) Caesarean Section |  |  |  | OB Cesarean Section -Pre Operative (multiphase) | Preoperative C-section obsetrical orders | no |  | yes
161 | 2 | OB FentaNYL for Pain Relief in Labour Clinical Protocol |  |  |  | DCW - ANES Labour Fentanyl Patient Controlled Analgesia (PCA) (Module).xlsm | Administration of fentanyl in labour | yes | Yes | no
162 | 2 | OB Self Administered Medication (SAM) Program (CKHA) Version 1 or Version 2 |  |  |  | No content | Postpartum orders | yes | Yes | yes
163 | 2 | OB Postpartum Orders: C-Section Delivery |  |  |  | DCW - OB Postpartum Cesarean Section (Multiphase).xlsm | Postpartum C-section delivery orders | no |  | yes
164 | 2 | OB Prevention of Mother to Infant Transmission of HIV Labour and Delivery |  |  |  | OB HIV Positive Intrapartum (Module) |  | no |  | no
165 | 2 | OB NIFEdipine Protocol Preterm Tocolysis |  |  |  | OB Preterm Labour (Module) | Nifedipine protocol preterm tocolysis | yes | Yes | yes
166 | 2 | OB Fallopian Tube Recanalization UHNBC |  |  |  |  | Fallopian Tube Recanalization
167 | 2 | OB MAGnesium Sulfate for Preeclampsia (Seizure Prevention) |  |  |  | DCW - OB Magnesium Sulfate Administration for Seizure Prevention (Module) CST-132026.xlsm | Hypertensive Disorders in Pregnancy - Antepartum | Yes, please pull the Mg orders from all three of the NH order sets per the comment | Yes | yes
168 | 2 | OB Bakri (Intrauterine) Balloon Monitoring |  |  |  |  | No NH content
169 | 2 | OB Stillbirth/Neonatal Death Investigations |  |  |  | OB Intrauterine Fetal Death Investigation (Module) | No NH content
170 | 2 | OB RhIG (RhoGAM) for Rh-negative pts (Opt: Kleihauer-Betke) |  |  |  |  | No NH content
171 | 2 | OB VTE Prophylaxis: Labour & Delivery Antepartum |  |  |  | VTE Prophylaxis (Enoxaparin) OB Antepartum- TSSO Zynx.docx | No NH content
172 | 2 | OB VTE Prophylaxis: Labour & Delivery POSTPARTUM |  |  |  | OB Postpartum VTE Thromboprophylaxis (Module) | No NH content
173 | 2 | OB Companion Well Baby |  |  |  | No CST content | Companion Well Baby orders | No |  | no
174 | 2 | URO Preoperative Non-Emergency Major Urological Surgery |  |  |  | URO Pre Procedure Enhanced Recovery After Surgery (ERAS) Pre Operative (Day of Surgery) | Preoperative Non-emergency Major Urological Surgery orders (UHNBC) | yes | Yes | no
175 | 2 | URO Postoperative Non-Emergency Major Urological Surgery |  |  |  | UROL Urology Day Surgery- Post Operative (Multiphase) | Postoperative Non-emergency Major Urological Surgery orders (UHNBC) | yes |  | no
176 | 2 | URO Day of Surgery Non-Emergency Major Urological Surgery |  |  |  | UROL Urology Day Surgery- Post Operative (Multiphase) | Day of Surgery Non-Emergency Major Urological Surgery Orders (UHNBC) | yes |  | no
177 | 2 | URO Post Percutaneous Nephrostomy Tube Insertion (with Joan) |  |  |  | No CST content | Post Percutnaeous Nephrostomy Tube Insertion orders (UHNBC) | Yes |  | no
178 | 2 | NEO Nutrition Bloodwork |  |  |  | Parenteral Nutrition Initiation (TPN)- Lab Collect Laboratory (Module) | Neonatal TPN bloodwork | yes |  | no
179 | 2 | NEO Infant Parenteral Nutrition |  |  |  | No Content | Neonatal-infant parenteral nutrition orders | no |  | yes
180 | 2 | PED Bronchiolitis (Jennifer Day reviewing) |  |  |  | DCW - PED ED Bronchiolitis.xlsm | was just approved, will update soon | no |  | yes
181 | 2 | PED Eating Disorders admission |  |  |  | PED MH Inpatient Eating Disorders (Module) | Pediatric Eating Disorder Admission | no |  | yes
182 | 2 | PED Parenteral Nutrition |  |  |  | no content | Pediatric Parenteral Nutrition orders | no |  | no
183 | 2 | PED MH admission |  |  |  | DCW- PED MH Child Psychiatry Admission (Multiphase) | Content just approved, will update soon | no |  | yes
184 | 2 | PED Febrile Neutropenia |  |  |  | Neutropenic Fever - Pediatric - Modular Zynx Content.docx | Pediatric Febrile Neutropenia | no |  | yes | Use NH content (especially for antibiotics)
185 | 2 | NEPH Chronic Hemodialysis |  |  |  | NEPH Hemodialysis 3 Days a Week Maintenance Treatment for 2 Months (Day of Treatment) | Chronic Hemodialysis orders | yes |  | yes | Not sure if day of treatment works with our build. Also attached TSSO Zynx version in comments
186 | 2 | NEPH Peritoneal Dialysis Peritonitis |  |  |  | NEPH Peritoneal Dialysis Peritonitis Empiric Treatment | Peritoneal Dialysis Peritonitis orders | yes |  | no
187 | 2 | NEPH Initial Renal Anemia Management Prescription |  |  |  | NEPH Hemodialysis Adjunct Medications | Initial Renal Anemia Management orders | yes |  | yes
188 | 2 | NEPH Alteplase Use for Occluded Hemodialysis Catheters |  |  |  | NEPH Alteplase for Partially Occluded Hemodialysis Arteriovenous Fistula or Graft | Alteplase use for occluded hemo catheters | no |  | yes
189 | 2 | NEPH Hemodialysis Treatment |  |  |  | NEPH Hemodialysis Initiation Treatent (Day of Treatment) | t | yes |  | no
190 | 3 | NEPH Insertion Tenckhoff Catheter |  |  |  | No CST content | Insertion Tenckhoff Catheter Nephrology preop orders | no |  | yes
191 | 3 | NEPH Chronic Peritoneal Dialysis (PD) |  |  |  | NEPH AMB Peritoneal Dialysis Chronic Maintenance Labs | Chronic Peritoneal Dialysis orders | yes |  | no
192 | 3 | NEPH NxStage Home Hemodialysis |  |  |  | No CST content | NxStage Home Hemodialysis orders | yes |  | no
193 | 3 | NEPH Insertion Tenckhoff Catheter Nephrology Postoperative |  |  |  | NEPH Peritoneal Dialysis Catheter Insertion (Multiphase) | Insertion Tenckhoff Catheter Nephrology post op orders | yes |  | no
194 | 3 | NEPH New Patient Post Catheter Insertion Prescription
195 | 3 | NEPH Bowel Care- Patients on Continuous Ambulatory Peritoneal Dialysis |  |  |  | No CST content | Adult Bowel Care Orders - patient on continuous ambulatory peritoneal dialysis | yes |  | no
196 | 3 | ORTHO Same Day Joint Replacement Postop |  |  |  | SURG ORTHO Joint Arthroplasty Same Day Home Phased - TSSO Zynx.docx
197 | 3 | ORTHO Hip and Knee Arthroplasty Post Op (Multiphase) |  |  |  | ORTHO Hip and Knee Arthroplasty -Post Operative (Multiphase)
198 | 3 | ORTHO Post-Operative Hip and Knee Protocol (Day2) | [8 empty] | Not sure if this needs to be on its own? Or part of post-op.
| 3 | ORTHO Arthroscopy Pre Op / Intra OP (Multiphase) |  |  |  | SURG ORTHO Arthroscopy PreopIntraop Phased GRHC Zynx.docx
199 | 3 | ORTHO Arthroscopy Post Op (Multiphase) |  |  |  | SURG ORTHO Arthroscopy Postop Phased- GRHC Zynx.docx
200 | 3 | ORTHO Post-Operative Arthroscopy (Shoulder) |  |  |  | DCW ORTHO Upper Extremity- Post Operative (Multiphase)
201 | 3 | ORTHO Pre Op Total Joint Replacement |  |  |  | DCW ORTHO Elective - Pre Op (Day of Surgery)
202 | 3 | SURG Day of Surgery Non-emergency Colon Resection |  |  |  | GENSURG Bowel Surgery (Enhanced REcovery AFter Surgery -ERAS)- Pre Op (Day of Surgery)
203 | 3 | SURG Preoperative Non-emergency Colon Resection |  |  |  | GENSURG Bowel Surgery (Enhanced Recovery After Surgery- ERAS)- - Pre Anesthesia Clinic
204 | 3 | SURG Postoperative Non-emergency Colon Resection |  |  |  | GENSURG Bowel Surgery (Enhanced Recovery After Surgery- ERAS)- post Operative (multiphase)
205 | 3 | SURG Leech Therapy |  |  |  | DCW PLASURG Leech Therapy | Leech Therapy orders fo venous congestion UHNBC | yes |  | yes
206 | 3 | SURG Hospital at Home Postoperative |  |  |  | No CST/Zynx content | H@H surgical admission orders UHNBC | no |  | yes
207 | 3 | ONC BCG |  |  |  | UROL AMB GUBCG Bladder Instillation Initial Treatment qweekly for 6 week (Day of Treatment) | BCG orders | no |  | Yes | Note this consistence of an initial treatment and then a maintenance treatment (both attached in CST column)
208 | 3 | Aminoglycosides/Gentamicin/Tobramycin & Therapeutic Drug Monitoring Subphase |  |  |  | Aminoglycoside (TobramycinGentamicinAmikacin) Management subphase KGH Zynx | Initiation of aminoglycosides for adults | yes |  | yes
209 | 3 | Vancomycin & Therapeutic Drug Monitoring Subphase |  |  |  | Vancomycin Infusion (Module) | Initiation of vancomycin for adults | yes |  | no
210 | 3 | Bowel Routine - Taking Opioid Subphase |  |  |  | DCW Bowel Protocol (Module) | Adult bowel care orders - patient taking daily opioid | yes |  | yes
211 | 3 | Bowel Routine - Not Taking Opioid Subphase |  |  |  | Bowel Routine Non-Opioid TSSO Zynx | Adult bowel care orders - patient not taking daily opioid | yes |  | yes
212 | 3 | Influenza Pneumococcal Vaccine |  |  |  | GEN Influenza Pneumococcal Vaccine Zynx | with HLS
#REF! | 3 | Vaccinations Post-Emergent Splenectomy Subphase |  |  |  | DCW TRAUMA Post Operative Vaccinations for Non-Elective Splenectormy (Module) | no NH content
|  | ORTHO Post Total Hip and Knee Arthroplasty VTE Prophylaxis |  |  |  | ORTHO Fractured Hip Venous Thromboembolism (VTE) Prophylaxis (Module) | VTE Prophylaxis Post Total Hip and Knee Arthroplasty
#REF! | 3 | SURG VTE Prophylaxis Subphase |  |  |  | Venous Thromboembolism (VTE) Prophylaxis- Surgery | No NH content
#REF! | 3 | OB VTE Prophylaxis Subphase |  |  |  | OB Postpartum VTE Thromboprophylaxis | no NH content
#REF! | 3 | Buprenorphine-naloxone (maintenance) Subphase |  |  |  | Buprenorphine- Naloxone (Suboxone) Maintenance | Content as above H42 | no |  | no
#REF! |  | PAL Palliative Sedation Therapy |  |  |  | PAL Palliative Sedation Therapy | No NH Content
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
(ID Plans are with Tyler and Patricia - in Word Format)
Note on P2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is a basic DCW based on CST, NH, and other relevant order sets. This will be based on a very basic crosswalk, removing coarse pieces of the CST order set such as services that aren't available in NH
Note on S2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Andrew will run a software program that will convert the DCW into an XML file that can be loaded into PowerChart
Note on C4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Andrew - do not enter fondaparinux, we do not use on our order sets. It can be entered separate as needed.
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rough conversion done - I will slot in NH content
Note on L5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rough conversion done - I will slot in NH content
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rough conversion done - I will slot in NH content
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated content since no access to floppy disc
Note on P8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] I can't see this content, but I went through the zynx and deleted/cleaned up if you want to use that to build DCW.
Note on H15: Clary, Kendra [NH]: Also have a discharge order
Note on G17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inserted DCW from C36 instead of DCW - ED Diabetic Ketoacidosis (DKA) - Adults 19 Years and Older.xlsm (then line 36 may be removed as a duplicate)
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Site specific for UHNBC. BVDH also has
Note on H18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PEDS only
Note on H19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NH has site specific orders
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Fix Naming Reply: Changed to reflect enteral nutrition with unblocking built in
Note on P28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is TIA @Deonarine, Andrew [NH]
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Was ED to Outpatient CST. Do we want an admission order? Changed to DCW - NEURO Stroke Management CST-171233.xlsm
Note on P30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not TIA plan @Deonarine, Andrew [NH]
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: site specific
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: duplicate of line 19?
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: see C19
Note on G39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NH does not use weight based dosing
Note on H43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: have others (2 in 1 solution etc. - 6 in total)
Note on L49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] our content is out of date so i think its ok to leave as CST for now :) Reply: @Deonarine, Andrew [NH] jk i cant read... i do have a screen shot of the adult CST content that we can have HLS create into a DCW?
Note on C53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I changed this name to NIA prefix
Note on G67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Separate CST orders for initiate, maintain, monitor
Note on L72: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DCW - ANES Labour Epidural Analgesia.xlsm
Note on H73: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://ournh.northernhealth.ca/oursites/collaboration/ordersets/Documents/11-111-5361%20Adult%20Epidural-Intrathecal%20Infusion%20Orders.pdf
Note on G82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] this should be the hypertonic saline 3% but the ED replacement is linked here (link in column N says hypertonic saline but content is ED elec replacement)
Note on P82: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Deonarine, Andrew [NH] title to match comment see cell F81
Note on P83: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Deonarine, Andrew [NH] this is RESP Thorocentesis, not Enteral Tube Feeds....and it is a duplicate-there is another RESP Thorocentesis at A100 Reply: Fixed @Stever, Suzy (Elizabeth) [NH] ! Reply: @Deonarine, Andrew [NH] I am not sure if the AMB enteral tube feeding multiphase is different than the enteral nutrition in B20 (I cannot access the F83 link) but perhaps we delete this one since it is the same as N20? Or were you wanting a multiphase DCW to try out here?
Note on L86: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: I just put that order set there as a template Reply: @Day, Jennifer [NH] - updated with a DCW I built from NYGH, so we're no longer using the wrong CST DCW
Note on H88: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: updated with current format for PP build
Note on G93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Title needs to change to match content
Note on L93: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Deonarine, Andrew [NH] should remove this CST link and the xml file as these are for the managed alcohol program (MAP) and we do not have a MAP in northern health right now so we cannot facilitate these orders until that program gets going. May be able to pull content for alcohol specific hepatitis but not likely a high priority build. Reply: @Granberg, Jessica - removed the CST link, I built a new DCW from NYGH for now so it's purely for alcoholic hepatitis rather than MAP
Note on L94: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CAP linked
Note on L95: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: Peds order set linked Reply: Hi @Day, Jennifer [NH] - I did a really basic conversion of the NH C.diff Order Set into a DCW - check out the NH DCW tab in the spreadsheet
Note on L96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Deonarine, Andrew [NH] Elaine Veldman, wound care nursing lead, wanted to have a look at these to make sure they match the BC provincial guidelines as she felt they could differ from the ones out East. Not a priority for this specific topic. Reply: Sounds good @Granberg, Jessica !
Note on L97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] Elaine Veldman, wound care nursing lead, wanted to have a look at these to make sure they match the BC provincial guidelines as she felt they could differ from the ones out East. Not a priority for this specific topic.
Note on H98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: site specific
Note on P99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] I renamed the DCW so the name matches the content.
Note on H100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: site specific to UHNBC
Note on L101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Granberg, Jessica - I put a *very* quick and dirty DCW built from NH here Reply: Perfect
Note on G103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: does not look like this was ever reviewed
Note on P103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Deonarine, Andrew [NH] name on DCW says potassium dialysate but content is thorocentesis. This may be one to build in Zynx/DCW since DCW pulled does not match what we are looking for
Note on P106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: renamed with (Thoracic) in title to indicate type of surgery
Note on P107: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: renamed with (Thoracic) in title to indicate type of surgery
Note on C141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Are these surgical orders?
Note on G164: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CST also has qweekly, q2weekly and qmonthly
Note on G172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NEPH AMB Intradialytic Parenteral Nutrition (Day of Treatment) https://healthbc.sharepoint.com/sites/SaferCare-ProjectNH/_layouts/15/Doc.aspx?sourcedoc={516BEB07-BD0D-427E-B547-8509EECA8FAF}&file=DCW%20-%20NEPH%20AMB%20Intradialytic%20Parenteral%20Nutrition%20(Day%20of%20Treatment).xlsm&action=default&mobileredirect=true&DefaultItemOpen=1
Note on G173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OB Postpartum Cesarean Section (Multiphase) https://healthbc.sharepoint.com/sites/SaferCare-ProjectNH/_layouts/15/Doc.aspx?sourcedoc={93C4D411-AD66-446E-A29F-73B18F00C74F}&file=DCW%20-%20OB%20Postpartum%20Cesarean%20Section%20(Multiphase).xlsm&action=default&mobileredirect=true&DefaultItemOpen=1
Note on C177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are under reconstruction -- there are infant, intrapartum, and postpartum orders for HIV + pts and high risk pts (6 in total)
Note on G177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OB HIV Positive Postpartum (Module) https://healthbc.sharepoint.com/sites/SaferCare-ProjectNH/_layouts/15/Doc.aspx?sourcedoc={CEE8E2C4-BDA3-4D23-9E49-8804C0F0348C}&file=DCW%20-%20OB%20HIV%20Positive%20Postpartum%20(Module)%20CST-132019.xlsm&action=default&mobileredirect=true&DefaultItemOpen=1
Note on C180: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are embbed in 3 different order sets (hytensive disorders in pregnancy: antepartum; intrapartum; post partum
Note on G182: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: OB Fetal Demise and/or Loss Greater than 13 Weeks (Multiphase) https://healthbc.sharepoint.com/sites/SaferCare-ProjectNH/_layouts/15/Doc.aspx?sourcedoc={4E78821C-5EDE-41D0-B599-9A9E89B16A7D}&file=DCW%20-%20OB%20Fetal%20Demise%20and%20%20or%20Loss%20Greater%20than%2013%20Weeks%20(Multiphase).xlsm&action=default&mobileredirect=true&DefaultItemOpen=1
Note on G198: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: RENAL Hemodialysis (WRH) TSSO Zynx.docx
Note on G204: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: labs NEPH Peritoneal Dialysis Catheter Occlusion Management https://healthbc.sharepoint.com/:x:/r/sites/SaferCare-ProjectNH/Shared%20Documents/CareOrders/04.%20Order%20Set%20Work/05.%20CST%20Materials/CSTDCWs/CST%20NEPH%20DCWs/DCW%20-%20NEPH%20Peritoneal%20Dialysis%20Catheter%20Occlusion%20Management.xlsm?d=w2c0f1af670554a3ab233a668a5921dee&csf=1&web=1&e=ZjfjZB
Note on C207: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can't find on OurNH, would we build a prescription?
Note on C209: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These are all site specific, need SNL direction
Note on G221: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: maintenance phase UROL AMB GUBCG Bladder Instillation Maintenance Treatment qmonthly for 12 month (Day of Treatment).xlsm
Note on C226: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: needs to be built, Zynx content

## Subphases
PED/NEO Code Status (Module)
NICU Small Baby Care (Less than 29 Weeks) (Module)
NICU Neurological Assessment (Neurovital Signs) (Module)
NICU Nutrition (Module)
PED/NEO TM Hepatitis B Immune Globulin IM (HbIG) (Module)
NICU Bovine Lipid Extract Surfactant (BLES) Administration (Module)
NICU Poractant Alfa (Curosurf) Administration (Module)
PED/NEO TM Red Blood Cell (RBC) Transfusion (Module)
NICU Lumbar Puncture (Module)
NICU Screening (Module)
NICU Management of Ventilation (Module)
Critical Care Goals | This is just under "patient care' in a NICU admission order but order sentence is quite specific
Additional IV Fluids (Module)
Replacement Fluids for NG Loss (Module)
Insulin Subcutaneous for Patients Eating or NPO (Sliding Scale) (Module)
Hypersensitivity / Anaphylaxis Treatment (Module)
Venous Thromboembolism (VTE) Prophylaxis - Surgery (Module)
Bowel Protocol - Surgical (Module)
Bowel Protocol (module)
ANES Respiratory Depression (Module)
ANES Epidural Discontinuation (Module)
DCW - ANES Multi-Modal Pain Management CST-175587.xlsm | for additional adjuvants (NSAIDs, acetaminophen), anti-nausea, antipruritics
ED Pain / Nausea / Vomiting (Module)
ED Intubation (Module)
PED ED Peripheral IV and IV Fluids (Module)
Additional IV Fluids (Module)
TM Plasma Transfusion (Frozen Plasma / FFP) (Module)
TM Red Blood Cell (RBC) Transfusion (Module)
TM Platelet Transfusion (Module)
TM Hepatitis B Immune Globulin IM (HbIG) (Module)
OB Postpartum VTE Thromboprophylaxis (Module) | Suzy built in Zynx
LAB - Pleural (Chest) Fluid Testing
Standard Weight Based IV Heparin Orders (STAGO) 10-111-5052 | Suzy built in Zynx
Low Target Heparin Orders 10-111-5082 | Suzy built in Zynx

## Comments
Date | Author | Comment
2023-01-26 | Andrew | CST has a chest pain order set which might be useful: ED Chest Pain

## Top30Word
NH Order set name | NH order set number | Need a word file?
Baricitinib Orders (For COVID-19 Only) | 10-800-5019 | With Andrew
COVID-19 Adult Admission Orders (non-ICU) For confirmed or suspected COVID-19 Cases | 10-800-5003 | With Andrew
COVID-19 Adult Palliative Care Orders (non-ICU) | 10-800-5004 | no
COVID-19 ER Lab Investigations - For confirmed or suspected COVID-19 | 10-800-5002 | no
COVID-19 Palliative Sedation and End of Life Orders | 10-800-5005 | yes
Inpatient COVID-19 Vaccine Orders (ages 5 and up) | 10-800-5016 | With Andrew
Intensive Care Admission Orders (For Covid-19 ONLY) | 10-800-5001 | no
LTC COVID-19 Booster Vaccine Order | 10-800-5023 | no
LTC COVID-19 Primary Series Vaccine Order | 10-800-5013 | no
Nirmatrelvir-Ritonavir Paxlovid Orders (For COVID-19) | 10-800-5024 | no
Remdesivir Infusion Orders (For COVID-19) | 10-800-5022 | With Andrew
Sotrovimab Infusion Orders (For COVID-19 Only) | 10-800-5021 | with Andrew
Tocilizumab Infusion Orders Critically ill (For COVID-19) | 10-800-5014 | with Andrew
Community Acquired Pneumonia | 10-111-5094 | No, with Andrew’s list | (sent as FSR example)
Subcutaneous Lidocaine Infusion Orders for Pain | 10-111-5359 | yes
Adult Ketamine Intravenous Infusion Orders for Chronic Refractory Neuropathic Pain | 10-111-5299 | yes
BCG Order Set | 10-111-5148 | no
Outpatient IV Antimicrobial Therapy | 10-111-5051 | no
Adult Eating Disorders Medical Stabilization Orders for Inpatient Admission | 10-111-5385 | no
Pediatric Eating Disorders Medical Stabilization | 10-111-5251 | no
Pediatric Asthma Emergency Management in Urgent or Emergent Settings Orders | 10-111-5320 | With Andrew
Pediatric Status Epilepticus | 10-111-5422 | no
Pediatric Sepsis 0 Days if Age to 28 Days of Age | 10-111-5389 | no
Pediatric Sepsis 29 Days of Age to 17 Years Less One Day | 10-111-5390 | With Andrew
Pediatric Code Trauma | 10-111-5404 | With Andrew
Telemetry Order Set | 10-111-5286 | yes
Preterm Premature Rupture of Membranes (PPROM) – Admission | 10-111-5388 | yes
Intrapartum Admission Orders | 10-111-5325 | yes
Percutaneous Radiologic Gastrostomy (PRG) Post-Procedure Orders | 10-111-5211 | yes

## PaperOrders
Order Set | Stakeholder...